## Detailed Gantt
Sprint | Hafta | Odak | Task | Diagram/Artifact | AI Tools | Dependencies | Deliverables
Sprint 1 | Hafta 1 | Product Discovery | User Stories | User Stories Doc | ChatGPT | - | User Stories
Sprint 1 | Hafta 1 | Product Discovery | SRS oluşturma | SRS.md | ChatGPT | User Stories | SRS
Sprint 1 | Hafta 1 | Product Discovery | Product Vision | Vision Doc | ChatGPT | SRS | Product Vision
Sprint 2 | Hafta 2 | System Design | Veri modeli | DB Schema | ChatGPT | SRS | Schema
Sprint 2 | Hafta 2 | System Design | ER Diagram | ER Diagram | dbdiagram.io | Schema | ERD
Sprint 2 | Hafta 2 | System Design | System Design | Architecture Doc | ChatGPT | ERD | System Design
Sprint 2 | Hafta 2 | System Design | External API kararı | Architecture Update | ChatGPT | System Design | Updated Design
Sprint 3 | Hafta 3 | API Design | API Contracts | API_CONTRACTS.md | ChatGPT | System Design | API Contracts
Sprint 3 | Hafta 3 | API Design | API Structure | API_STRUCTURE.md | ChatGPT | API Contracts | API Structure
Sprint 3 | Hafta 3 | API Design | Game Flow | Flow Diagram | Miro | API Structure | Game Flow
Sprint 3 | Hafta 3 | API Design | External API plan | Integration Doc | ChatGPT | Game Flow | Integration Plan
Sprint 4 | Hafta 4 | Backend Setup | NestJS setup | Project Structure | Cursor | API Structure | Backend Skeleton
Sprint 4 | Hafta 4 | Backend Setup | Prisma setup | Schema.prisma | Cursor | Backend Skeleton | ORM Setup
Sprint 4 | Hafta 4 | Backend Setup | Supabase connection | DB Connection | Supabase | Prisma | DB Connected
Sprint 4 | Hafta 4 | Backend Setup | Migration | Migration Files | Prisma CLI | DB Connected | Tables
Sprint 5 | Hafta 5 | Backend Core | Auth module | Auth APIs | Cursor | DB | Auth Working
Sprint 5 | Hafta 5 | Backend Core | Child module | Child APIs | Cursor | Auth | Child CRUD
Sprint 5 | Hafta 5 | Backend Core | GameSession | Session Logic | Cursor | Child | Session Tracking
Sprint 5 | Hafta 5 | Backend Core | Games proxy | External API | Cursor | API | Games Fetch
Sprint 5 | Hafta 5 | Backend Core | Analytics logic | Skill Logic | ChatGPT | Session | Analytics Base
Sprint 6 | Hafta 6 | Parent UX | Dashboard | Wireframe | Figma | Analytics | Dashboard UI
Sprint 6 | Hafta 6 | Parent UX | Child detail | Wireframe | Figma | Dashboard | Child UI
Sprint 6 | Hafta 6 | Parent UX | Skill charts | Charts UI | Figma | Analytics | Charts
Sprint 6 | Hafta 6 | Parent UX | Reports | Report UI | Figma | Charts | Reports
Sprint 7 | Hafta 7 | Child UX | Game selection | Wireframe | Figma | Games API | Game UI
Sprint 7 | Hafta 7 | Child UX | Redirect flow | Flow | Figma | Game UI | Flow
Sprint 7 | Hafta 7 | Child UX | Feedback | UI | Figma | Session | Feedback
Sprint 7 | Hafta 7 | Child UX | Fun UX | UX Design | Figma | Feedback | UX
Sprint 8 | Hafta 8 | Frontend | Auth screens | UI | Cursor | Backend | Auth UI
Sprint 8 | Hafta 8 | Frontend | Parent UI | UI | Cursor | Backend | Dashboard UI
Sprint 8 | Hafta 8 | Frontend | Child flow | UI | Cursor | Backend | Child Flow
Sprint 8 | Hafta 8 | Frontend | API integration | Integration | Cursor | API | Connected UI
Sprint 9 | Hafta 9 | Analytics | Skill charts | Charts | Chart.js | Data | Charts
Sprint 9 | Hafta 9 | Analytics | Reports | Reports | Chart.js | Charts | Reports
Sprint 9 | Hafta 9 | Analytics | Notifications | System | Backend | Events | Notifications
Sprint 10 | Hafta 10 | Final | Testing | Test Docs | Postman | All | Test Results
Sprint 10 | Hafta 10 | Final | Bug fixing | Fixes | Cursor | Testing | Stable App
Sprint 10 | Hafta 10 | Final | Performance | Optimization | Cursor | Backend | Optimized
Sprint 10 | Hafta 10 | Final | Demo | Presentation | PowerPoint | All | MVP Demo